## Norms & Assumptions
PINE FELLING PRODUCTION PLAN – NORMS & ASSUMPTIONS
Nkomati Mine, Mpumalanga, South Africa ¦ Equipment: Stihl MS 382 ¦ Mon–Fri 07:00–15:30
SECTION 1 – PROJECT SCHEDULE & STAFFING
Parameter | Value | Unit | Notes
Project Start Date | 2026-03-30 | date | First working day on site
Phase 2 Start (4 operators) | 2026-04-08 | date | 2 additional operators join
Operators – Phase 1 (30 Mar – 07 Apr) | 2 | operators | 2 chainsaw operators
Operators – Phase 2 (08 Apr onwards) | 4 | operators | 4 chainsaw operators total
Shift start | 07:00 | hh:mm | 07:00 daily
Shift end | 15:30 | hh:mm | 15:30 daily
Working hours per shift | 8.5 | hrs | 07:00–15:30 gross
Effective cutting hours | 6.5 | hrs | Excl. travel, fueling, sharpening, breaks
Working days | Mon–Fri |  | Excluding SA public holidays
SECTION 2 – 2026 SA PUBLIC HOLIDAYS (Days NOT worked)
Date | Holiday | Day | Impact on Schedule
2026-01-01 | New Year's Day | Thursday | Before project start
2026-03-21 | Human Rights Day | Saturday | Before project start
2026-04-03 | Good Friday | Friday | ⚠ Project day lost – no production
2026-04-06 | Family Day (Easter Monday) | Monday | ⚠ Project day lost – no production
2026-04-27 | Freedom Day | Monday | ⚠ Project day lost – no production
2026-05-01 | Workers' Day | Friday | ⚠ Project day lost – no production
2026-06-16 | Youth Day | Tuesday | ⚠ Project day lost – no production
2026-08-09 | National Women's Day | Sunday | ⚠ Project day lost – no production
2026-09-24 | Heritage Day | Thursday | ⚠ Project day lost – no production
2026-12-16 | Day of Reconciliation | Wednesday | ⚠ Project day lost – no production
2026-12-25 | Christmas Day | Friday | ⚠ Project day lost – no production
2026-12-26 | Day of Goodwill | Saturday | ⚠ Project day lost – no production
SECTION 3 – SA CHAINSAW FELLING NORMS (Stihl MS 382)
Parameter | Value | Unit | Source / Notes
Trees felled per operator per day | 150 | trees/day | SA Forestry norm – clear-fell pine, flat-moderate terrain
Avg tree volume – mature pine >15yr | 0.35 | m³/tree | FSA guideline, Mpumalanga pine 25–35cm DBH
Avg tree volume – young pine <15yr | 0.18 | m³/tree | FSA guideline, smaller diameter stands
Target m³ per operator per day | 52.5 | m³/day | 150 trees x 0.35 m3 (mature pine)
Average trees per hectare | 800 | trees/ha | Plantation norm; adjust per compartment
Terrain adjustment – hilly/sloped | 0.85 | factor | 15% reduction for difficult terrain
SECTION 4 – CONSUMABLES NORMS (per operator per day, Stihl MS 382)
Parameter | Value | Unit | Notes
2-stroke fuel mix (50:1) | 2.5 | litres/day | Petrol + 2T oil mixed 50:1
Bar & chain oil | 1.2 | litres/day | Automatic oiler consumption
Saw chains (replacements) | 0.5 | chains/day | ~1 chain per 2 days hard cutting
Cutting guide bar (wear) | 0.05 | bars/day | Replace approx every 20 working days
PPE – gloves (pairs) | 0.2 | pairs/day | Replace every 5 days
File (chain sharpening 4mm) | 0.2 | files/day | 4mm round file for MS 382
Spark plugs | 0.05 | plugs/day | Replace every 20 days
Air filter | 0.033 | filters/day | Replace every 30 days
COLOUR LEGEND
Blue cells |  |  | User input cells – enter your data here
Grey cells |  |  | Calculated formula cells – do not edit
Orange cells |  |  | SA Public Holiday – no production day
Light green |  |  | Phase 2 rows (4 operators from 08 Apr)

## Project Schedule
PROJECT SCHEDULE – DAY-BY-DAY PRODUCTION CALENDAR
Start: 30 Mar 2026 ¦ Phase 1: 2 operators ¦ Phase 2 from 08 Apr: 4 operators ¦ Mon–Fri 07:00–15:30 ¦ SA Holidays excluded
PHASE 1 (30 Mar – 07 Apr 2026) – 2 Operators | [5 empty] | PHASE 2 (08 Apr 2026 onwards) – 4 Operators
Day | Date | Day of Week | Status | Operators Working | Target Trees/Day | Target m³/Day | Actual Trees | Actual m³ | Tree Variance | m³ Variance | Achievement % | Notes
1 | 2026-03-30 | Monday | Phase 1 – Working Day 1 | 2 | 300 | 0.36
2 | 2026-03-31 | Tuesday | Phase 1 – Working Day 2 | 2 | 300 | 0.36
3 | 2026-04-01 | Wednesday | Phase 1 – Working Day 3 | 2 | 300 | 0.36
4 | 2026-04-02 | Thursday | Phase 1 – Working Day 4 | 2 | 300 | 0.36
| 2026-04-03 | Friday | 🏖 Good Friday | 0 | 0 | 0
| 2026-04-04 | Saturday | Weekend | 0 | 0 | 0
| 2026-04-05 | Sunday | Weekend | 0 | 0 | 0
| 2026-04-06 | Monday | 🏖 Family Day (Easter Monday) | 0 | 0 | 0
5 | 2026-04-07 | Tuesday | Phase 1 – Working Day 5 | 2 | 300 | 0.36
6 | 2026-04-08 | Wednesday | Phase 2 – Working Day 6 | 4 | 600 | 0.72
7 | 2026-04-09 | Thursday | Phase 2 – Working Day 7 | 4 | 600 | 0.72
8 | 2026-04-10 | Friday | Phase 2 – Working Day 8 | 4 | 600 | 0.72
| 2026-04-11 | Saturday | Weekend | 0 | 0 | 0
| 2026-04-12 | Sunday | Weekend | 0 | 0 | 0
9 | 2026-04-13 | Monday | Phase 2 – Working Day 9 | 4 | 600 | 0.72
10 | 2026-04-14 | Tuesday | Phase 2 – Working Day 10 | 4 | 600 | 0.72
11 | 2026-04-15 | Wednesday | Phase 2 – Working Day 11 | 4 | 600 | 0.72
12 | 2026-04-16 | Thursday | Phase 2 – Working Day 12 | 4 | 600 | 0.72
13 | 2026-04-17 | Friday | Phase 2 – Working Day 13 | 4 | 600 | 0.72
| 2026-04-18 | Saturday | Weekend | 0 | 0 | 0
| 2026-04-19 | Sunday | Weekend | 0 | 0 | 0
14 | 2026-04-20 | Monday | Phase 2 – Working Day 14 | 4 | 600 | 0.72
15 | 2026-04-21 | Tuesday | Phase 2 – Working Day 15 | 4 | 600 | 0.72
16 | 2026-04-22 | Wednesday | Phase 2 – Working Day 16 | 4 | 600 | 0.72
17 | 2026-04-23 | Thursday | Phase 2 – Working Day 17 | 4 | 600 | 0.72
18 | 2026-04-24 | Friday | Phase 2 – Working Day 18 | 4 | 600 | 0.72
| 2026-04-25 | Saturday | Weekend | 0 | 0 | 0
| 2026-04-26 | Sunday | Weekend | 0 | 0 | 0
| 2026-04-27 | Monday | 🏖 Freedom Day | 0 | 0 | 0
19 | 2026-04-28 | Tuesday | Phase 2 – Working Day 19 | 4 | 600 | 0.72
20 | 2026-04-29 | Wednesday | Phase 2 – Working Day 20 | 4 | 600 | 0.72
21 | 2026-04-30 | Thursday | Phase 2 – Working Day 21 | 4 | 600 | 0.72
| 2026-05-01 | Friday | 🏖 Workers' Day | 0 | 0 | 0
| 2026-05-02 | Saturday | Weekend | 0 | 0 | 0
| 2026-05-03 | Sunday | Weekend | 0 | 0 | 0
22 | 2026-05-04 | Monday | Phase 2 – Working Day 22 | 4 | 600 | 0.72
23 | 2026-05-05 | Tuesday | Phase 2 – Working Day 23 | 4 | 600 | 0.72
24 | 2026-05-06 | Wednesday | Phase 2 – Working Day 24 | 4 | 600 | 0.72
25 | 2026-05-07 | Thursday | Phase 2 – Working Day 25 | 4 | 600 | 0.72
26 | 2026-05-08 | Friday | Phase 2 – Working Day 26 | 4 | 600 | 0.72
| 2026-05-09 | Saturday | Weekend | 0 | 0 | 0
| 2026-05-10 | Sunday | Weekend | 0 | 0 | 0
27 | 2026-05-11 | Monday | Phase 2 – Working Day 27 | 4 | 600 | 0.72
28 | 2026-05-12 | Tuesday | Phase 2 – Working Day 28 | 4 | 600 | 0.72
29 | 2026-05-13 | Wednesday | Phase 2 – Working Day 29 | 4 | 600 | 0.72
30 | 2026-05-14 | Thursday | Phase 2 – Working Day 30 | 4 | 600 | 0.72
31 | 2026-05-15 | Friday | Phase 2 – Working Day 31 | 4 | 600 | 0.72
| 2026-05-16 | Saturday | Weekend | 0 | 0 | 0
| 2026-05-17 | Sunday | Weekend | 0 | 0 | 0
32 | 2026-05-18 | Monday | Phase 2 – Working Day 32 | 4 | 600 | 0.72
33 | 2026-05-19 | Tuesday | Phase 2 – Working Day 33 | 4 | 600 | 0.72
34 | 2026-05-20 | Wednesday | Phase 2 – Working Day 34 | 4 | 600 | 0.72
35 | 2026-05-21 | Thursday | Phase 2 – Working Day 35 | 4 | 600 | 0.72
36 | 2026-05-22 | Friday | Phase 2 – Working Day 36 | 4 | 600 | 0.72
| 2026-05-23 | Saturday | Weekend | 0 | 0 | 0
| 2026-05-24 | Sunday | Weekend | 0 | 0 | 0
37 | 2026-05-25 | Monday | Phase 2 – Working Day 37 | 4 | 600 | 0.72
38 | 2026-05-26 | Tuesday | Phase 2 – Working Day 38 | 4 | 600 | 0.72
39 | 2026-05-27 | Wednesday | Phase 2 – Working Day 39 | 4 | 600 | 0.72
40 | 2026-05-28 | Thursday | Phase 2 – Working Day 40 | 4 | 600 | 0.72
41 | 2026-05-29 | Friday | Phase 2 – Working Day 41 | 4 | 600 | 0.72
| 2026-05-30 | Saturday | Weekend | 0 | 0 | 0
| 2026-05-31 | Sunday | Weekend | 0 | 0 | 0
42 | 2026-06-01 | Monday | Phase 2 – Working Day 42 | 4 | 600 | 0.72
43 | 2026-06-02 | Tuesday | Phase 2 – Working Day 43 | 4 | 600 | 0.72
44 | 2026-06-03 | Wednesday | Phase 2 – Working Day 44 | 4 | 600 | 0.72
45 | 2026-06-04 | Thursday | Phase 2 – Working Day 45 | 4 | 600 | 0.72
46 | 2026-06-05 | Friday | Phase 2 – Working Day 46 | 4 | 600 | 0.72
| 2026-06-06 | Saturday | Weekend | 0 | 0 | 0
| 2026-06-07 | Sunday | Weekend | 0 | 0 | 0
47 | 2026-06-08 | Monday | Phase 2 – Working Day 47 | 4 | 600 | 0.72
48 | 2026-06-09 | Tuesday | Phase 2 – Working Day 48 | 4 | 600 | 0.72
49 | 2026-06-10 | Wednesday | Phase 2 – Working Day 49 | 4 | 600 | 0.72
50 | 2026-06-11 | Thursday | Phase 2 – Working Day 50 | 4 | 600 | 0.72
51 | 2026-06-12 | Friday | Phase 2 – Working Day 51 | 4 | 600 | 0.72
| 2026-06-13 | Saturday | Weekend | 0 | 0 | 0
| 2026-06-14 | Sunday | Weekend | 0 | 0 | 0
52 | 2026-06-15 | Monday | Phase 2 – Working Day 52 | 4 | 600 | 0.72
| 2026-06-16 | Tuesday | 🏖 Youth Day | 0 | 0 | 0
53 | 2026-06-17 | Wednesday | Phase 2 – Working Day 53 | 4 | 600 | 0.72
54 | 2026-06-18 | Thursday | Phase 2 – Working Day 54 | 4 | 600 | 0.72
55 | 2026-06-19 | Friday | Phase 2 – Working Day 55 | 4 | 600 | 0.72
| 2026-06-20 | Saturday | Weekend | 0 | 0 | 0
| 2026-06-21 | Sunday | Weekend | 0 | 0 | 0
56 | 2026-06-22 | Monday | Phase 2 – Working Day 56 | 4 | 600 | 0.72
57 | 2026-06-23 | Tuesday | Phase 2 – Working Day 57 | 4 | 600 | 0.72
58 | 2026-06-24 | Wednesday | Phase 2 – Working Day 58 | 4 | 600 | 0.72
59 | 2026-06-25 | Thursday | Phase 2 – Working Day 59 | 4 | 600 | 0.72
60 | 2026-06-26 | Friday | Phase 2 – Working Day 60 | 4 | 600 | 0.72
| 2026-06-27 | Saturday | Weekend | 0 | 0 | 0
| 2026-06-28 | Sunday | Weekend | 0 | 0 | 0
61 | 2026-06-29 | Monday | Phase 2 – Working Day 61 | 4 | 600 | 0.72
62 | 2026-06-30 | Tuesday | Phase 2 – Working Day 62 | 4 | 600 | 0.72
63 | 2026-07-01 | Wednesday | Phase 2 – Working Day 63 | 4 | 600 | 0.72
64 | 2026-07-02 | Thursday | Phase 2 – Working Day 64 | 4 | 600 | 0.72
65 | 2026-07-03 | Friday | Phase 2 – Working Day 65 | 4 | 600 | 0.72
| 2026-07-04 | Saturday | Weekend | 0 | 0 | 0
| 2026-07-05 | Sunday | Weekend | 0 | 0 | 0
66 | 2026-07-06 | Monday | Phase 2 – Working Day 66 | 4 | 600 | 0.72
67 | 2026-07-07 | Tuesday | Phase 2 – Working Day 67 | 4 | 600 | 0.72
68 | 2026-07-08 | Wednesday | Phase 2 – Working Day 68 | 4 | 600 | 0.72
69 | 2026-07-09 | Thursday | Phase 2 – Working Day 69 | 4 | 600 | 0.72
70 | 2026-07-10 | Friday | Phase 2 – Working Day 70 | 4 | 600 | 0.72
| 2026-07-11 | Saturday | Weekend | 0 | 0 | 0
| 2026-07-12 | Sunday | Weekend | 0 | 0 | 0
71 | 2026-07-13 | Monday | Phase 2 – Working Day 71 | 4 | 600 | 0.72
72 | 2026-07-14 | Tuesday | Phase 2 – Working Day 72 | 4 | 600 | 0.72
73 | 2026-07-15 | Wednesday | Phase 2 – Working Day 73 | 4 | 600 | 0.72
74 | 2026-07-16 | Thursday | Phase 2 – Working Day 74 | 4 | 600 | 0.72
75 | 2026-07-17 | Friday | Phase 2 – Working Day 75 | 4 | 600 | 0.72
| 2026-07-18 | Saturday | Weekend | 0 | 0 | 0
| 2026-07-19 | Sunday | Weekend | 0 | 0 | 0
76 | 2026-07-20 | Monday | Phase 2 – Working Day 76 | 4 | 600 | 0.72
77 | 2026-07-21 | Tuesday | Phase 2 – Working Day 77 | 4 | 600 | 0.72
78 | 2026-07-22 | Wednesday | Phase 2 – Working Day 78 | 4 | 600 | 0.72
79 | 2026-07-23 | Thursday | Phase 2 – Working Day 79 | 4 | 600 | 0.72
80 | 2026-07-24 | Friday | Phase 2 – Working Day 80 | 4 | 600 | 0.72
| 2026-07-25 | Saturday | Weekend | 0 | 0 | 0
| 2026-07-26 | Sunday | Weekend | 0 | 0 | 0
81 | 2026-07-27 | Monday | Phase 2 – Working Day 81 | 4 | 600 | 0.72
82 | 2026-07-28 | Tuesday | Phase 2 – Working Day 82 | 4 | 600 | 0.72
83 | 2026-07-29 | Wednesday | Phase 2 – Working Day 83 | 4 | 600 | 0.72
84 | 2026-07-30 | Thursday | Phase 2 – Working Day 84 | 4 | 600 | 0.72
85 | 2026-07-31 | Friday | Phase 2 – Working Day 85 | 4 | 600 | 0.72
| 2026-08-01 | Saturday | Weekend | 0 | 0 | 0
| 2026-08-02 | Sunday | Weekend | 0 | 0 | 0
86 | 2026-08-03 | Monday | Phase 2 – Working Day 86 | 4 | 600 | 0.72
87 | 2026-08-04 | Tuesday | Phase 2 – Working Day 87 | 4 | 600 | 0.72
88 | 2026-08-05 | Wednesday | Phase 2 – Working Day 88 | 4 | 600 | 0.72
89 | 2026-08-06 | Thursday | Phase 2 – Working Day 89 | 4 | 600 | 0.72
90 | 2026-08-07 | Friday | Phase 2 – Working Day 90 | 4 | 600 | 0.72
| 2026-08-08 | Saturday | Weekend | 0 | 0 | 0
| 2026-08-09 | Sunday | 🏖 National Women's Day | 0 | 0 | 0
91 | 2026-08-10 | Monday | Phase 2 – Working Day 91 | 4 | 600 | 0.72
92 | 2026-08-11 | Tuesday | Phase 2 – Working Day 92 | 4 | 600 | 0.72
93 | 2026-08-12 | Wednesday | Phase 2 – Working Day 93 | 4 | 600 | 0.72
94 | 2026-08-13 | Thursday | Phase 2 – Working Day 94 | 4 | 600 | 0.72
95 | 2026-08-14 | Friday | Phase 2 – Working Day 95 | 4 | 600 | 0.72
| 2026-08-15 | Saturday | Weekend | 0 | 0 | 0
| 2026-08-16 | Sunday | Weekend | 0 | 0 | 0
96 | 2026-08-17 | Monday | Phase 2 – Working Day 96 | 4 | 600 | 0.72
97 | 2026-08-18 | Tuesday | Phase 2 – Working Day 97 | 4 | 600 | 0.72
98 | 2026-08-19 | Wednesday | Phase 2 – Working Day 98 | 4 | 600 | 0.72
99 | 2026-08-20 | Thursday | Phase 2 – Working Day 99 | 4 | 600 | 0.72
100 | 2026-08-21 | Friday | Phase 2 – Working Day 100 | 4 | 600 | 0.72
| 2026-08-22 | Saturday | Weekend | 0 | 0 | 0
| 2026-08-23 | Sunday | Weekend | 0 | 0 | 0
101 | 2026-08-24 | Monday | Phase 2 – Working Day 101 | 4 | 600 | 0.72
102 | 2026-08-25 | Tuesday | Phase 2 – Working Day 102 | 4 | 600 | 0.72
103 | 2026-08-26 | Wednesday | Phase 2 – Working Day 103 | 4 | 600 | 0.72
104 | 2026-08-27 | Thursday | Phase 2 – Working Day 104 | 4 | 600 | 0.72
105 | 2026-08-28 | Friday | Phase 2 – Working Day 105 | 4 | 600 | 0.72
| 2026-08-29 | Saturday | Weekend | 0 | 0 | 0
| 2026-08-30 | Sunday | Weekend | 0 | 0 | 0
106 | 2026-08-31 | Monday | Phase 2 – Working Day 106 | 4 | 600 | 0.72
107 | 2026-09-01 | Tuesday | Phase 2 – Working Day 107 | 4 | 600 | 0.72
108 | 2026-09-02 | Wednesday | Phase 2 – Working Day 108 | 4 | 600 | 0.72
109 | 2026-09-03 | Thursday | Phase 2 – Working Day 109 | 4 | 600 | 0.72
110 | 2026-09-04 | Friday | Phase 2 – Working Day 110 | 4 | 600 | 0.72
| 2026-09-05 | Saturday | Weekend | 0 | 0 | 0
| 2026-09-06 | Sunday | Weekend | 0 | 0 | 0
111 | 2026-09-07 | Monday | Phase 2 – Working Day 111 | 4 | 600 | 0.72
112 | 2026-09-08 | Tuesday | Phase 2 – Working Day 112 | 4 | 600 | 0.72
113 | 2026-09-09 | Wednesday | Phase 2 – Working Day 113 | 4 | 600 | 0.72
114 | 2026-09-10 | Thursday | Phase 2 – Working Day 114 | 4 | 600 | 0.72
115 | 2026-09-11 | Friday | Phase 2 – Working Day 115 | 4 | 600 | 0.72
| 2026-09-12 | Saturday | Weekend | 0 | 0 | 0
| 2026-09-13 | Sunday | Weekend | 0 | 0 | 0
116 | 2026-09-14 | Monday | Phase 2 – Working Day 116 | 4 | 600 | 0.72
117 | 2026-09-15 | Tuesday | Phase 2 – Working Day 117 | 4 | 600 | 0.72
118 | 2026-09-16 | Wednesday | Phase 2 – Working Day 118 | 4 | 600 | 0.72
119 | 2026-09-17 | Thursday | Phase 2 – Working Day 119 | 4 | 600 | 0.72
120 | 2026-09-18 | Friday | Phase 2 – Working Day 120 | 4 | 600 | 0.72
| 2026-09-19 | Saturday | Weekend | 0 | 0 | 0
| 2026-09-20 | Sunday | Weekend | 0 | 0 | 0
121 | 2026-09-21 | Monday | Phase 2 – Working Day 121 | 4 | 600 | 0.72
122 | 2026-09-22 | Tuesday | Phase 2 – Working Day 122 | 4 | 600 | 0.72
123 | 2026-09-23 | Wednesday | Phase 2 – Working Day 123 | 4 | 600 | 0.72
| 2026-09-24 | Thursday | 🏖 Heritage Day | 0 | 0 | 0
124 | 2026-09-25 | Friday | Phase 2 – Working Day 124 | 4 | 600 | 0.72
| 2026-09-26 | Saturday | Weekend | 0 | 0 | 0
| 2026-09-27 | Sunday | Weekend | 0 | 0 | 0
125 | 2026-09-28 | Monday | Phase 2 – Working Day 125 | 4 | 600 | 0.72
126 | 2026-09-29 | Tuesday | Phase 2 – Working Day 126 | 4 | 600 | 0.72
127 | 2026-09-30 | Wednesday | Phase 2 – Working Day 127 | 4 | 600 | 0.72
128 | 2026-10-01 | Thursday | Phase 2 – Working Day 128 | 4 | 600 | 0.72
129 | 2026-10-02 | Friday | Phase 2 – Working Day 129 | 4 | 600 | 0.72
| 2026-10-03 | Saturday | Weekend | 0 | 0 | 0
| 2026-10-04 | Sunday | Weekend | 0 | 0 | 0
130 | 2026-10-05 | Monday | Phase 2 – Working Day 130 | 4 | 600 | 0.72
131 | 2026-10-06 | Tuesday | Phase 2 – Working Day 131 | 4 | 600 | 0.72
132 | 2026-10-07 | Wednesday | Phase 2 – Working Day 132 | 4 | 600 | 0.72
133 | 2026-10-08 | Thursday | Phase 2 – Working Day 133 | 4 | 600 | 0.72
134 | 2026-10-09 | Friday | Phase 2 – Working Day 134 | 4 | 600 | 0.72
| 2026-10-10 | Saturday | Weekend | 0 | 0 | 0
| 2026-10-11 | Sunday | Weekend | 0 | 0 | 0
135 | 2026-10-12 | Monday | Phase 2 – Working Day 135 | 4 | 600 | 0.72
136 | 2026-10-13 | Tuesday | Phase 2 – Working Day 136 | 4 | 600 | 0.72
137 | 2026-10-14 | Wednesday | Phase 2 – Working Day 137 | 4 | 600 | 0.72
138 | 2026-10-15 | Thursday | Phase 2 – Working Day 138 | 4 | 600 | 0.72
139 | 2026-10-16 | Friday | Phase 2 – Working Day 139 | 4 | 600 | 0.72
| 2026-10-17 | Saturday | Weekend | 0 | 0 | 0
| 2026-10-18 | Sunday | Weekend | 0 | 0 | 0
140 | 2026-10-19 | Monday | Phase 2 – Working Day 140 | 4 | 600 | 0.72
141 | 2026-10-20 | Tuesday | Phase 2 – Working Day 141 | 4 | 600 | 0.72
142 | 2026-10-21 | Wednesday | Phase 2 – Working Day 142 | 4 | 600 | 0.72
143 | 2026-10-22 | Thursday | Phase 2 – Working Day 143 | 4 | 600 | 0.72
144 | 2026-10-23 | Friday | Phase 2 – Working Day 144 | 4 | 600 | 0.72
| 2026-10-24 | Saturday | Weekend | 0 | 0 | 0
| 2026-10-25 | Sunday | Weekend | 0 | 0 | 0
145 | 2026-10-26 | Monday | Phase 2 – Working Day 145 | 4 | 600 | 0.72
146 | 2026-10-27 | Tuesday | Phase 2 – Working Day 146 | 4 | 600 | 0.72
147 | 2026-10-28 | Wednesday | Phase 2 – Working Day 147 | 4 | 600 | 0.72
148 | 2026-10-29 | Thursday | Phase 2 – Working Day 148 | 4 | 600 | 0.72
149 | 2026-10-30 | Friday | Phase 2 – Working Day 149 | 4 | 600 | 0.72
| 2026-10-31 | Saturday | Weekend | 0 | 0 | 0
PROJECT TOTALS |  |  |  |  | 87900 | 105.48 | 0 | 0 | 0 | 0 | 0%

## Compartment Targets
COMPARTMENT PRODUCTION TARGETS – PINE CLEAR FELLING
Nkomati Mine, Mpumalanga ¦ Start: 30 Mar 2026 ¦ All targets per SA Forestry Norms
COMPARTMENT |  | VOLUME & TREE ESTIMATES |  |  |  | PHASE 1 (2 operators) |  |  | PHASE 2 (4 operators from 08 Apr)
# | Compartment / Block | Area (ha) | Trees/ha | Est. Trees | Est. Vol (m³) | Ph1 Target Days | Ph1 Target End Date | Ph1 Trees /Op/Day | Ph2 Target Days | Ph2 Target End Date | Ph2 Trees /Op/Day
1 | A |  | 800 |  |  |  |  | 150 |  |  | 150
2 | B |  | 800 |  |  |  |  | 150 |  |  | 150
3 | C |  | 800 |  |  |  |  | 150 |  |  | 150
4 | D |  | 800 |  |  |  |  | 150 |  |  | 150
5 | Block 12.68ha | 12.68 | 800 | 10144 | 3550.4 | 34 |  | 150 | 17 |  | 150
6 | Block 3.97ha | 3.97 | 800 | 3176 | 1111.6 | 11 |  | 150 | 6 |  | 150
7 | Block 2.40ha | 2.4 | 800 | 1920 | 672 | 7 |  | 150 | 4 |  | 150
8 | Block 0.863ha | 0.863 | 800 | 690.4 | 241.64 | 3 |  | 150 | 2 |  | 150
9 | Block 2.503ha | 2.503 | 800 | 2002.4 | 700.84 | 7 |  | 150 | 4 |  | 150
10 | Block 0.317ha | 0.317 | 800 | 253.6 | 88.76 | 1 |  | 150 | 1 |  | 150
11 | Block 5ha (est) | 5 | 800 | 4000 | 1400 | 14 |  | 150 | 7 |  | 150
12 | 42.9ha – Outside fence | 42.9 | 800 | 34320 | 12012 | 115 |  | 150 | 58 |  | 150
13 | 14.9ha – Outside fence | 14.9 | 800 | 11920 | 4172 | 40 |  | 150 | 20 |  | 150
TOTALS |  | 85.533 |  | 68426.4 | 23949.24
⚠ Compartments A, B, C, D: Enter exact hectares in blue cells (Col C). Trees/ha (Col D) can be adjusted per stand inventory. Phase 1 = 2 operators (30 Mar–07 Apr) ¦ Phase 2 = 4 operators (08 Apr+)

## Operator Daily Log
OPERATOR DAILY LOG – INDIVIDUAL PERFORMANCE TRACKER
One row per operator per day ¦ Blue cells = enter actual values
# | Date | Operator Name | Compartment | Chainsaw Serial # | Target Trees/Day | Actual Trees | Target m³/Day | Actual m³ | Tree Var | m³ Var | Achievement % | Notes / Issues
1 |  |  |  |  | 150 |  | 0.18
2 |  |  |  |  | 150 |  | 0.18
3 |  |  |  |  | 150 |  | 0.18
4 |  |  |  |  | 150 |  | 0.18
5 |  |  |  |  | 150 |  | 0.18
6 |  |  |  |  | 150 |  | 0.18
7 |  |  |  |  | 150 |  | 0.18
8 |  |  |  |  | 150 |  | 0.18
9 |  |  |  |  | 150 |  | 0.18
10 |  |  |  |  | 150 |  | 0.18
11 |  |  |  |  | 150 |  | 0.18
12 |  |  |  |  | 150 |  | 0.18
13 |  |  |  |  | 150 |  | 0.18
14 |  |  |  |  | 150 |  | 0.18
15 |  |  |  |  | 150 |  | 0.18
16 |  |  |  |  | 150 |  | 0.18
17 |  |  |  |  | 150 |  | 0.18
18 |  |  |  |  | 150 |  | 0.18
19 |  |  |  |  | 150 |  | 0.18
20 |  |  |  |  | 150 |  | 0.18
21 |  |  |  |  | 150 |  | 0.18
22 |  |  |  |  | 150 |  | 0.18
23 |  |  |  |  | 150 |  | 0.18
24 |  |  |  |  | 150 |  | 0.18
25 |  |  |  |  | 150 |  | 0.18
26 |  |  |  |  | 150 |  | 0.18
27 |  |  |  |  | 150 |  | 0.18
28 |  |  |  |  | 150 |  | 0.18
29 |  |  |  |  | 150 |  | 0.18
30 |  |  |  |  | 150 |  | 0.18
31 |  |  |  |  | 150 |  | 0.18
32 |  |  |  |  | 150 |  | 0.18
33 |  |  |  |  | 150 |  | 0.18
34 |  |  |  |  | 150 |  | 0.18
35 |  |  |  |  | 150 |  | 0.18
36 |  |  |  |  | 150 |  | 0.18
37 |  |  |  |  | 150 |  | 0.18
38 |  |  |  |  | 150 |  | 0.18
39 |  |  |  |  | 150 |  | 0.18
40 |  |  |  |  | 150 |  | 0.18
41 |  |  |  |  | 150 |  | 0.18
42 |  |  |  |  | 150 |  | 0.18
43 |  |  |  |  | 150 |  | 0.18
44 |  |  |  |  | 150 |  | 0.18
45 |  |  |  |  | 150 |  | 0.18
46 |  |  |  |  | 150 |  | 0.18
47 |  |  |  |  | 150 |  | 0.18
48 |  |  |  |  | 150 |  | 0.18
49 |  |  |  |  | 150 |  | 0.18
50 |  |  |  |  | 150 |  | 0.18
51 |  |  |  |  | 150 |  | 0.18
52 |  |  |  |  | 150 |  | 0.18
53 |  |  |  |  | 150 |  | 0.18
54 |  |  |  |  | 150 |  | 0.18
55 |  |  |  |  | 150 |  | 0.18
56 |  |  |  |  | 150 |  | 0.18
57 |  |  |  |  | 150 |  | 0.18
58 |  |  |  |  | 150 |  | 0.18
59 |  |  |  |  | 150 |  | 0.18
60 |  |  |  |  | 150 |  | 0.18
61 |  |  |  |  | 150 |  | 0.18
62 |  |  |  |  | 150 |  | 0.18
63 |  |  |  |  | 150 |  | 0.18
64 |  |  |  |  | 150 |  | 0.18
65 |  |  |  |  | 150 |  | 0.18
66 |  |  |  |  | 150 |  | 0.18
67 |  |  |  |  | 150 |  | 0.18
68 |  |  |  |  | 150 |  | 0.18
69 |  |  |  |  | 150 |  | 0.18
70 |  |  |  |  | 150 |  | 0.18
71 |  |  |  |  | 150 |  | 0.18
72 |  |  |  |  | 150 |  | 0.18
73 |  |  |  |  | 150 |  | 0.18
74 |  |  |  |  | 150 |  | 0.18
75 |  |  |  |  | 150 |  | 0.18
76 |  |  |  |  | 150 |  | 0.18
77 |  |  |  |  | 150 |  | 0.18
78 |  |  |  |  | 150 |  | 0.18
79 |  |  |  |  | 150 |  | 0.18
80 |  |  |  |  | 150 |  | 0.18
81 |  |  |  |  | 150 |  | 0.18
82 |  |  |  |  | 150 |  | 0.18
83 |  |  |  |  | 150 |  | 0.18
84 |  |  |  |  | 150 |  | 0.18
85 |  |  |  |  | 150 |  | 0.18
86 |  |  |  |  | 150 |  | 0.18
87 |  |  |  |  | 150 |  | 0.18
88 |  |  |  |  | 150 |  | 0.18
89 |  |  |  |  | 150 |  | 0.18
90 |  |  |  |  | 150 |  | 0.18
91 |  |  |  |  | 150 |  | 0.18
92 |  |  |  |  | 150 |  | 0.18
93 |  |  |  |  | 150 |  | 0.18
94 |  |  |  |  | 150 |  | 0.18
95 |  |  |  |  | 150 |  | 0.18
96 |  |  |  |  | 150 |  | 0.18
97 |  |  |  |  | 150 |  | 0.18
98 |  |  |  |  | 150 |  | 0.18
99 |  |  |  |  | 150 |  | 0.18
100 |  |  |  |  | 150 |  | 0.18
101 |  |  |  |  | 150 |  | 0.18
102 |  |  |  |  | 150 |  | 0.18
103 |  |  |  |  | 150 |  | 0.18
104 |  |  |  |  | 150 |  | 0.18
105 |  |  |  |  | 150 |  | 0.18
106 |  |  |  |  | 150 |  | 0.18
107 |  |  |  |  | 150 |  | 0.18
108 |  |  |  |  | 150 |  | 0.18
109 |  |  |  |  | 150 |  | 0.18
110 |  |  |  |  | 150 |  | 0.18
111 |  |  |  |  | 150 |  | 0.18
112 |  |  |  |  | 150 |  | 0.18
113 |  |  |  |  | 150 |  | 0.18
114 |  |  |  |  | 150 |  | 0.18
115 |  |  |  |  | 150 |  | 0.18
116 |  |  |  |  | 150 |  | 0.18
117 |  |  |  |  | 150 |  | 0.18
118 |  |  |  |  | 150 |  | 0.18
119 |  |  |  |  | 150 |  | 0.18
120 |  |  |  |  | 150 |  | 0.18
PERIOD TOTALS |  |  |  |  | 18000 | 0 | 21.6 | 0 |  |  | 0%

## Consumables Tracker
CONSUMABLES DAILY TRACKER – ACTUAL vs TARGET USAGE
Operators working auto-adjusts: 2 ops before 08 Apr ¦ 4 ops from 08 Apr onwards
# | Date | Consumable Item | Unit | Target/Op/Day | Operators Working | Total Target /Day | Actual Issued | Variance | Notes
1 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
2 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
3 | 0 | Saw chains | chains | 0.5 | 2 | 1
4 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
5 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
6 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
7 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
8 | 0 | Air filter | filters | 0.033 | 2 | 0.066
9 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
10 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
11 | 0 | Saw chains | chains | 0.5 | 2 | 1
12 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
13 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
14 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
15 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
16 | 0 | Air filter | filters | 0.033 | 2 | 0.066
17 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
18 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
19 | 0 | Saw chains | chains | 0.5 | 2 | 1
20 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
21 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
22 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
23 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
24 | 0 | Air filter | filters | 0.033 | 2 | 0.066
25 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
26 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
27 | 0 | Saw chains | chains | 0.5 | 2 | 1
28 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
29 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
30 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
31 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
32 | 0 | Air filter | filters | 0.033 | 2 | 0.066
33 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
34 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
35 | 0 | Saw chains | chains | 0.5 | 2 | 1
36 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
37 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
38 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
39 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
40 | 0 | Air filter | filters | 0.033 | 2 | 0.066
41 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
42 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
43 | 0 | Saw chains | chains | 0.5 | 2 | 1
44 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
45 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
46 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
47 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
48 | 0 | Air filter | filters | 0.033 | 2 | 0.066
49 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
50 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
51 | 0 | Saw chains | chains | 0.5 | 2 | 1
52 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
53 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
54 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
55 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
56 | 0 | Air filter | filters | 0.033 | 2 | 0.066
57 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
58 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
59 | 0 | Saw chains | chains | 0.5 | 2 | 1
60 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
61 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
62 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
63 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
64 | 0 | Air filter | filters | 0.033 | 2 | 0.066
65 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
66 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
67 | 0 | Saw chains | chains | 0.5 | 2 | 1
68 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
69 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
70 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
71 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
72 | 0 | Air filter | filters | 0.033 | 2 | 0.066
73 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
74 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
75 | 0 | Saw chains | chains | 0.5 | 2 | 1
76 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
77 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
78 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
79 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
80 | 0 | Air filter | filters | 0.033 | 2 | 0.066
81 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
82 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
83 | 0 | Saw chains | chains | 0.5 | 2 | 1
84 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
85 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
86 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
87 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
88 | 0 | Air filter | filters | 0.033 | 2 | 0.066
89 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
90 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
91 | 0 | Saw chains | chains | 0.5 | 2 | 1
92 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
93 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
94 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
95 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
96 | 0 | Air filter | filters | 0.033 | 2 | 0.066
97 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
98 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
99 | 0 | Saw chains | chains | 0.5 | 2 | 1
100 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
101 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
102 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
103 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
104 | 0 | Air filter | filters | 0.033 | 2 | 0.066
105 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
106 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
107 | 0 | Saw chains | chains | 0.5 | 2 | 1
108 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
109 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
110 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
111 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
112 | 0 | Air filter | filters | 0.033 | 2 | 0.066
113 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
114 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
115 | 0 | Saw chains | chains | 0.5 | 2 | 1
116 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
117 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
118 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
119 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
120 | 0 | Air filter | filters | 0.033 | 2 | 0.066
121 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
122 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
123 | 0 | Saw chains | chains | 0.5 | 2 | 1
124 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
125 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
126 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
127 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
128 | 0 | Air filter | filters | 0.033 | 2 | 0.066
129 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
130 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
131 | 0 | Saw chains | chains | 0.5 | 2 | 1
132 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
133 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
134 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
135 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
136 | 0 | Air filter | filters | 0.033 | 2 | 0.066
137 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
138 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
139 | 0 | Saw chains | chains | 0.5 | 2 | 1
140 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
141 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
142 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
143 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
144 | 0 | Air filter | filters | 0.033 | 2 | 0.066
145 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
146 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
147 | 0 | Saw chains | chains | 0.5 | 2 | 1
148 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
149 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
150 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
151 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
152 | 0 | Air filter | filters | 0.033 | 2 | 0.066
153 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
154 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
155 | 0 | Saw chains | chains | 0.5 | 2 | 1
156 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
157 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
158 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
159 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
160 | 0 | Air filter | filters | 0.033 | 2 | 0.066
161 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
162 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
163 | 0 | Saw chains | chains | 0.5 | 2 | 1
164 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
165 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
166 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
167 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
168 | 0 | Air filter | filters | 0.033 | 2 | 0.066
169 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
170 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
171 | 0 | Saw chains | chains | 0.5 | 2 | 1
172 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
173 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
174 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
175 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
176 | 0 | Air filter | filters | 0.033 | 2 | 0.066
177 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
178 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
179 | 0 | Saw chains | chains | 0.5 | 2 | 1
180 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
181 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
182 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
183 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
184 | 0 | Air filter | filters | 0.033 | 2 | 0.066
185 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
186 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
187 | 0 | Saw chains | chains | 0.5 | 2 | 1
188 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
189 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
190 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
191 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
192 | 0 | Air filter | filters | 0.033 | 2 | 0.066
193 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
194 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
195 | 0 | Saw chains | chains | 0.5 | 2 | 1
196 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
197 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
198 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
199 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
200 | 0 | Air filter | filters | 0.033 | 2 | 0.066
201 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
202 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
203 | 0 | Saw chains | chains | 0.5 | 2 | 1
204 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
205 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
206 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
207 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
208 | 0 | Air filter | filters | 0.033 | 2 | 0.066
209 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
210 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
211 | 0 | Saw chains | chains | 0.5 | 2 | 1
212 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
213 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
214 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
215 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
216 | 0 | Air filter | filters | 0.033 | 2 | 0.066
217 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
218 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
219 | 0 | Saw chains | chains | 0.5 | 2 | 1
220 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
221 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
222 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
223 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
224 | 0 | Air filter | filters | 0.033 | 2 | 0.066
225 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
226 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
227 | 0 | Saw chains | chains | 0.5 | 2 | 1
228 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
229 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
230 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
231 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
232 | 0 | Air filter | filters | 0.033 | 2 | 0.066
233 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
234 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
235 | 0 | Saw chains | chains | 0.5 | 2 | 1
236 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
237 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
238 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
239 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
240 | 0 | Air filter | filters | 0.033 | 2 | 0.066
241 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
242 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
243 | 0 | Saw chains | chains | 0.5 | 2 | 1
244 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
245 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
246 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
247 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
248 | 0 | Air filter | filters | 0.033 | 2 | 0.066
249 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
250 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
251 | 0 | Saw chains | chains | 0.5 | 2 | 1
252 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
253 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
254 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
255 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
256 | 0 | Air filter | filters | 0.033 | 2 | 0.066
257 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
258 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
259 | 0 | Saw chains | chains | 0.5 | 2 | 1
260 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
261 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
262 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
263 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
264 | 0 | Air filter | filters | 0.033 | 2 | 0.066
265 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
266 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
267 | 0 | Saw chains | chains | 0.5 | 2 | 1
268 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
269 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
270 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
271 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
272 | 0 | Air filter | filters | 0.033 | 2 | 0.066
273 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
274 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
275 | 0 | Saw chains | chains | 0.5 | 2 | 1
276 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
277 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
278 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
279 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
280 | 0 | Air filter | filters | 0.033 | 2 | 0.066
281 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
282 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
283 | 0 | Saw chains | chains | 0.5 | 2 | 1
284 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
285 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
286 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
287 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
288 | 0 | Air filter | filters | 0.033 | 2 | 0.066
289 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
290 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
291 | 0 | Saw chains | chains | 0.5 | 2 | 1
292 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
293 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
294 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
295 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
296 | 0 | Air filter | filters | 0.033 | 2 | 0.066
297 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
298 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
299 | 0 | Saw chains | chains | 0.5 | 2 | 1
300 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
301 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
302 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
303 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
304 | 0 | Air filter | filters | 0.033 | 2 | 0.066
305 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
306 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
307 | 0 | Saw chains | chains | 0.5 | 2 | 1
308 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
309 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
310 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
311 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
312 | 0 | Air filter | filters | 0.033 | 2 | 0.066
313 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
314 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
315 | 0 | Saw chains | chains | 0.5 | 2 | 1
316 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
317 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
318 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
319 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
320 | 0 | Air filter | filters | 0.033 | 2 | 0.066
321 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
322 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
323 | 0 | Saw chains | chains | 0.5 | 2 | 1
324 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
325 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
326 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
327 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
328 | 0 | Air filter | filters | 0.033 | 2 | 0.066
329 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
330 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
331 | 0 | Saw chains | chains | 0.5 | 2 | 1
332 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
333 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
334 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
335 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
336 | 0 | Air filter | filters | 0.033 | 2 | 0.066
337 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
338 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
339 | 0 | Saw chains | chains | 0.5 | 2 | 1
340 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
341 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
342 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
343 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
344 | 0 | Air filter | filters | 0.033 | 2 | 0.066
345 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
346 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
347 | 0 | Saw chains | chains | 0.5 | 2 | 1
348 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
349 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
350 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
351 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
352 | 0 | Air filter | filters | 0.033 | 2 | 0.066
353 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
354 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
355 | 0 | Saw chains | chains | 0.5 | 2 | 1
356 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
357 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
358 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
359 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
360 | 0 | Air filter | filters | 0.033 | 2 | 0.066
361 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
362 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
363 | 0 | Saw chains | chains | 0.5 | 2 | 1
364 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
365 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
366 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
367 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
368 | 0 | Air filter | filters | 0.033 | 2 | 0.066
369 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
370 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
371 | 0 | Saw chains | chains | 0.5 | 2 | 1
372 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
373 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
374 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
375 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
376 | 0 | Air filter | filters | 0.033 | 2 | 0.066
377 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
378 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
379 | 0 | Saw chains | chains | 0.5 | 2 | 1
380 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
381 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
382 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
383 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
384 | 0 | Air filter | filters | 0.033 | 2 | 0.066
385 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
386 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
387 | 0 | Saw chains | chains | 0.5 | 2 | 1
388 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
389 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
390 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
391 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
392 | 0 | Air filter | filters | 0.033 | 2 | 0.066
393 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
394 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
395 | 0 | Saw chains | chains | 0.5 | 2 | 1
396 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
397 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
398 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
399 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
400 | 0 | Air filter | filters | 0.033 | 2 | 0.066
401 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
402 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
403 | 0 | Saw chains | chains | 0.5 | 2 | 1
404 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
405 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
406 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
407 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
408 | 0 | Air filter | filters | 0.033 | 2 | 0.066
409 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
410 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
411 | 0 | Saw chains | chains | 0.5 | 2 | 1
412 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
413 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
414 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
415 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
416 | 0 | Air filter | filters | 0.033 | 2 | 0.066
417 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
418 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
419 | 0 | Saw chains | chains | 0.5 | 2 | 1
420 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
421 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
422 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
423 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
424 | 0 | Air filter | filters | 0.033 | 2 | 0.066
425 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
426 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
427 | 0 | Saw chains | chains | 0.5 | 2 | 1
428 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
429 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
430 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
431 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
432 | 0 | Air filter | filters | 0.033 | 2 | 0.066
433 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
434 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
435 | 0 | Saw chains | chains | 0.5 | 2 | 1
436 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
437 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
438 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
439 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
440 | 0 | Air filter | filters | 0.033 | 2 | 0.066
441 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
442 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
443 | 0 | Saw chains | chains | 0.5 | 2 | 1
444 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
445 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
446 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
447 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
448 | 0 | Air filter | filters | 0.033 | 2 | 0.066
449 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
450 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
451 | 0 | Saw chains | chains | 0.5 | 2 | 1
452 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
453 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
454 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
455 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
456 | 0 | Air filter | filters | 0.033 | 2 | 0.066
457 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
458 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
459 | 0 | Saw chains | chains | 0.5 | 2 | 1
460 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
461 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
462 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
463 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
464 | 0 | Air filter | filters | 0.033 | 2 | 0.066
465 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
466 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
467 | 0 | Saw chains | chains | 0.5 | 2 | 1
468 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
469 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
470 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
471 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
472 | 0 | Air filter | filters | 0.033 | 2 | 0.066
473 |  | Fuel mix (2-stroke 50:1) | litres | 2.5 | 2 | 5
474 | 0 | Bar & chain oil | litres | 1.2 | 2 | 2.4
475 | 0 | Saw chains | chains | 0.5 | 2 | 1
476 | 0 | Guide bar | bars | 0.05 | 2 | 0.1
477 | 0 | Gloves (pairs) | pairs | 0.2 | 2 | 0.4
478 | 0 | Round file (4mm) | files | 0.2 | 2 | 0.4
479 | 0 | Spark plug | plugs | 0.05 | 2 | 0.1
480 | 0 | Air filter | filters | 0.033 | 2 | 0.066
Formulas:
Date = [Date, row above]

## Performance Dashboard
PERFORMANCE DASHBOARD – PROJECT SUMMARY
Auto-calculated from Project Schedule & Operator Log ¦ Start: 30 Mar 2026
PROJECT INFORMATION
Project Start Date | 30 March 2026
Phase 1 (2 operators) | 30 Mar – 07 Apr 2026 | Mon–Fri 07:00–15:30
Phase 2 (4 operators) | 08 Apr 2026 onwards | Mon–Fri 07:00–15:30
Shift Hours | 07:00 – 15:30 | 8.5 hrs gross ¦ 6.5 hrs effective cutting
Equipment | Stihl MS 382 | One saw per operator (SA OHS)
SA Holidays in project | 10 | Days with zero production
PRODUCTION KPIs (from Project Schedule)
KPI | Target | Actual | Variance | Status
Total Trees – Target (Project) | 87900 | 0 | -87900 | ⚠ BELOW TARGET
Total Volume m³ – Target | 105.48 | 0 | -105.48 | ⚠ BELOW TARGET
Overall Achievement % | 100% | 0% | -100% | ⚠ BELOW TARGET
Working Days – Phase 1 (2 ops) | 5 | → Enter actuals | — | —
Working Days – Phase 2 (4 ops) | See Project Schedule | → Enter actuals | — | —
Phase 1 Cumulative Target Trees | 1500 | → Enter actuals | — | —
Phase 1 Cumulative Target m³ | 525.0 | → Enter actuals | — | —
PHASE PRODUCTION SUMMARY
Phase | Period | Operators | Working Days | Trees Target
Phase 1 | 30 Mar – 07 Apr 2026 | 2 | 5 | 1500
Phase 2 | 08 Apr 2026 onwards | 4 | See Schedule | Per schedule
HOW TO USE THIS WORKBOOK
1. NORMS & ASSUMPTIONS: Review SA norms, SA holiday list, and project schedule dates.
2. PROJECT SCHEDULE: This is your master calendar. Enter actual trees felled & m³ per working day (blue cells).
3. COMPARTMENT TARGETS: Enter exact hectares for blocks A–D. Adjust trees/ha per stand inventory.
4. OPERATOR DAILY LOG: Log individual operator performance (one row per person per day).
5. CONSUMABLES TRACKER: Enter daily consumables issued. Operators auto-adjust by date phase.
6. PERFORMANCE DASHBOARD: Summarises everything – review weekly for corrective actions.